# DESCRIPTION OF THE PROPOSED PROJECT	CHAPTER 2

Eskom, as the primary supplier of electricity in South Africa, is currently responding to the growing electricity demand and predicted future demand within South Africa through the establishment of new generation and transmission capacity in South Africa.

Eskom uses a modelling tool called Integrated Strategic Electricity Planning (ISEP) to plan its future capacity strategy.  By analysing usage patterns and growth trends in the economy, and matching these with the performance features of various generation technologies and demand side management options, ISEP identifies the timing, quantity and type (base load or peaking) of new generation capacity options required in the long-term.  These options include the return-to-service of the three mothballed coal-fired Simunye Power Stations (i.e. Camden, Komati and Grootvlei), the establishment of new coal fired power plants, pumped storage schemes, gas-fired power plants, nuclear plants, renewable energy technologies (mainly wind and solar projects), and import options within the Southern African Power Pool.  As the older Eskom power plants reach the end of their design life from approximately 2025 onwards, the use of all available technologies will need to be exploited to replace these in order to supply the country’s growing electricity demand.

As part of its capacity expansion programme, Eskom is currently constructing the new Medupi coal-fired power station, in the Lephalale area of the Limpopo Province.  In order to integrate this power station into the electricity transmission grid, Eskom Transmission is considering linkages to various points within the electricity transmission system.  In order to support the upsurge in demand for the Platinum group metals in the Mokopane area, and to improve the reliability of electricity supply to the Polokwane area, Eskom Transmission is proposing the introduction of the Mokopane Integration project.  This project includes the construction of the following:

- A new transmission substation on a site near Mokopane.

- Two 400 kV transmission power lines running in parallel looping in and out of one of the existing Matimba-Witkop 400kV transmission lines (i.e. two lines in parallel for a distance of up to 10 km) in order to integrate the new substation into the transmission system.

- Two new 765 kV transmission power lines running in parallel between the Delta Substation (a new substation to be located near the Medupi Power Station) and the existing Witkop Substation (near Polokwane), as follows:

- A new 765kV transmission power line between the Delta Substation and the new Mokopane Substation (a distance of approximately 150 km); and a new 765kV transmission power line between the new Mokopane Substation and the Witkop Substation (a distance of approximately 
60 km).

- A new 765kV transmission power line between Delta Substation and the Witkop Substation (a distance of approximately 200 km).

- Associated works to integrate the new transmission power lines and substation into the Transmission grid (such as access roads, communication tower, etc) and accommodate the new lines at existing substations (such as the construction of new feeder bays within the existing Witkop substation site).

The background to the selection of reasonable and feasible alternatives for the proposed substation and turn-in lines and extension of the Witkop Substation is discussed in a separate Draft Scoping Report (Reference Number 12/12/20/1187).

This chapter of this report provides the background to the selection of reasonable and feasible alternatives for the proposed 765kV transmission power lines (Reference Number 12/12/20/1140).

## 2.1.	The Need for the Proposed 765 kV Transmission Power Lines

Studies have shown a steady 1 000 MW per annum average load growth for the period 2006 to 2025 in the National Transmission System.  This is due to industrialisation, urban growth and electrification.  It is also a sign of good economic growth in the whole country.  Through strategic studies undertaken, Eskom predicts that this load growth will continue, which will result in the need for additional generation capacity by the year 2012.  In order to meet this demand, Eskom requires additional generation capacity that needs to be transmitted to load centres throughout the Eskom Transmission System.  An unreliable Transmission system could hamper growth in the country

Eskom Transmission has taken measures to get the most out of the existing Transmission system so that the construction of the new lines will occur only when needed.  These measures include:

- Comprehensive checks on the existing lines to ensure that they are within the legal clearance for overhead lines.  Lines sag when placed under heavy load conditions, due to heating of the conductors.

- Installation of line monitoring devices that measures the atmospheric conditions prevailing.  This allows Eskom Transmission to decide whether the lines can cope with more loading (e.g. on a cold day the line can be loaded to more than usual levels since the lines cool down and they do not sag as much).

- Installation of new infrastructure

- Demand side management

- The best reinforcement options are selected to ensure that an optimised mix of cost, technical benefit and environmental impact was achieved.

As all options for optimisation of the existing infrastructure have already been studied and implemented, new transmission power lines will be required to be constructed.  The new transmission lines will be brought into operation at the time when the load growth and demand exceeds the supply, i.e. by 2012.  It is therefore necessary to secure the necessary servitudes timeously, to ensure this will be possible.

A definite twofold need for new transmission power lines has therefore been identified:

- to optimise the existing system and

- to increase line capacity in the Transmission system.

By increasing the supply into the Transmission system, the foreseen load growth can be addressed in a suitable and economical way.  Optimisation of the current system is currently underway, and would alleviate some problems in the system.  The medium to long term load requirements can be addressed by the increased supply due to the new transmission power lines.

## 2.2.	Alternatives for Satisfying the Additional Power Need

The following alternatives for satisfying the twofold need for additional electrical supply to the Transmission system and optimising the existing infrastructure were investigated by Eskom Transmission:

### 2.2.1.	The Do Nothing Option

The do nothing option would be the option of not constructing any new transmission power lines.  By not taking any action, Eskom Transmission may end with a situation of not being able to ensure firm supply into some parts of the country in the very near future.  This would eventually lead to load shedding which can cause major disruptions of power supply to different areas at different times.  This can have a significant impact on the economy of the country, as no real economic growth would be able to take place without additional electricity supply.  This option is therefore rejected as a feasible alternative as it would neither supply the projected demand for electricity nor optimise the existing infrastructure.

### 2.2.2.	Demand Side Management

Demand Side Management (DSM) can generally be defined as the activities performed by the electricity supply utility, which are designed to produce the desired changes in the load shape through influencing customer usage of electricity and to reduce overall demand by more efficient use.  These efforts are intended to produce a flat load duration curve to ensure the most efficient use of installed network capacity.

By reducing peak demand and shifting load from high load to low load periods, reductions in capital expenditure (for network capacity expansion) and operating costs can be achieved.  Some of the basic tools are the price signals (such as time of use tariffs) given by the utility and direct load management.  This option is practised to a certain extent, but is not considered to be a feasible option for expansion in the Mokopane and Polokwane region as it is considered to be un-sustainable in the long-term.

### 2.2.3	New Generation Systems

Medupi coal-fired power station is currently under construction in the Lephalale area and is planned for commissioning by 2012.Confirmed  Power from this power station will be required to be transmitted to the load centres some hundreds of kilometres away from the Lephalale area.  Transmitting power through Transmission power lines is currently the most economical way to supply bulk electricity.

The existing Transmission power lines from the Lephalale area cannot evacuate the additional 4 500 MW of power from the new Medupi Power Station without violating network reliability and integrity.  As all options for optimisation of the existing infrastructure have already been studied and implemented, new transmission power lines are required to feed electricity from Medupi Power Station to Transmission substations, including the proposed Mokopane and existing Witkop substations in the Mokopane and Polokwane areas.

### 2.2.4.	Upgrade Existing Transmission Power Lines by using Bigger Conductors

This option would result in the physical load on the existing towers increasing substantially.  The existing towers would be inadequate to support this physical load.  Furthermore, it would not be possible to remove one transmission power line from service to perform the upgrading work, as the remaining supply lines would not be able to supply the electrical loads in the Transmission system.  The power from the Medupi Power Station would not be able to be evacuated to the load centres without causing dynamic instability in the Eskom network which could result in black-outs.  This option would not improve the reliability of the Transmission system nor be sustainable.

### 2.2.5.	Construct New Transmission Power Lines between Medupi Power Station and the Mokopane Area and Witkop Substation

This alternative is part of the new generation capacity alternatives.  The need for increased capacity and the need for optimising existing infrastructure would be met through the implementation of this option.  The advantages associated with this option are as follows:

- It overcomes the line overloading problems.

- It will create a more flexible network since it forms an interconnection between the loads fed from Medupi (and the planned Mmamabula Power Station in Botswana) and the Generation area of Mpumalanga.  This will improve the overall reliability of the Transmission system, which will be of benefit to both Eskom and to all electricity users in the area.

- It will improve the angular stability of the Lephalale generation pool.

Due to current land use and development in the country very little open corridors remain that could be utilised to install major Transmission power lines.  New routes must however be secured to ensure servitudes for the expansion of the network and to be able to meet the forecast increase in demand.  Therefore, Eskom are proposing that two new 765kV power lines be constructed between the Medupi Power Station and the Mokopane and Polokwane areas.  These power lines would be initially operated as 400 kV lines, but would be able to be operated as 765kV lines in the future should additional power be generated in the Lephalale area.

The need for increased capacity and the need for optimising existing infrastructure will be met through the implementation of this option, and therefore this option is nominated as the most feasible option by Eskom Transmission to compliment new generation planned at Medupi Power Station.

## 2.3.	Identification and Description of Alternative Transmission Power Line Development Corridors

From the analysis of the various alternatives to satisfy the need for additional power transmission capacity, Eskom Transmission determined that the introduction of the Mokopane Integration Project was the most feasible and cost-effective solution in order to transmit the power generated at the Medupi power station to the load centres in the Mokopane and Polokwane areas.  This project involves construction of the following:

- Two new 765 kV transmission power lines running in parallel between the Delta Substation (a new substation to be located near the Medupi Power Station) and the existing Witkop Substation (near Polokwane), as follows:

- A new 765kV transmission power line between the Delta Substation and the new Mokopane Substation (a distance of approximately 150 km); and a new 765kV transmission power line between the new Mokopane Substation and the Witkop Substation (a distance of approximately 
60 km).

- A new 765kV transmission power line between Delta Substation and the Witkop Substation (a distance of approximately 200 km).

- Associated works to integrate the new transmission lines into the Transmission grid (such as access roads).

The following technical requirements were considered in the identification of feasible corridors for the establishment of the required transmission power lines:

- Technically viable and cost effective corridors of approximately 5 km in width were identified.

- As far as possible, the servitude lengths between power supply and load points should be minimised.

- As far as possible, the number and magnitude of angles along the line should be minimised in order to allow the use of less expensive and visually less-intrusive tower types.

- Crossing over of existing major power lines should be avoided as far as possible as this increases the potential for technical incidents during operation.

- The alignment should cater for known topographical/terrain constraints of the tower types to be used, and soil conditions for the foundations in terms of geotechnical suitability and costs.

- The proposed alignment should provide for the need of appropriate access roads to the servitude and tower positions for the both construction and maintenance/operation phases.

- Care should be taken to avoid the following as far as tower positioning and access road construction are concerned:

  - extensive rock outcrops;

  - rugged terrain, hills and mountains;

  - active clay soil, vleis and floodplains;

  - potential unstable side-slope terrain; and

  - eroded and unstable areas.

- Other issues which technically affect the location of a transmission power line include:

  - agricultural lands, in particular those under irrigation;

  - large water bodies;

  - open-cast mining;

  - crossing points with roads, rail and telecommunication lines at off-set angles less than 60.

- The following obvious and observable environmental issues should be taken into account:

  - human settlements and communities;

  - land use (where possible);

  - passing between water bodies (bird flight paths usually extend between water bodies);

  - ecologically sensitive areas;

  - scenic areas with high visual/aesthetic quality; and

  - untransformed indigenous vegetation.

Technically feasible alternative transmission power line development corridors have been identified for investigation within the EIA process (refer to Figure 2.1).  These alternative power line alternatives are described in further detail below.

Corridor 1 leaves the Medupi Power station in an easterly direction south of Lephalale before traversing the D'Nyala Nature Reserve.  It crosses the Waterberg plateau, Waterberg Biosphere Reserve buffer zone (Touchstone Nature Reserve) and the Biosphere Reserve's core area (Moepel Farms) before spanning across the escarpment and dropping down towards the R518.  It continues for an additional 46km before joining the existing Matimba-Witkop transmission lines.  The total length of this corridor is 160km.

Corridor 2 originates at the Medupi Power Station and proceeds in a north-easterly direction for approximately 30km before veering east for 85km.  It traverses the Waterberg Biosphere Reserve's transitional zone and the southern section of the Wonderkop Nature Reserve before it turns south-east, crossing the southern section of the Bellevue Nature Reserve.  It continues for roughly 82km before joining the Matimba-Witkop power lines near the proposed Mokopane substation site.  The total length of the transmission line corridor is approximately 190km.

Corridor 3 leaves the Medupi Power Station in a south-easterly direction traversing rough terrain (valleys and ridges near Mokolo River) before continuing over the Waterberg plateau.  It crosses into the Waterberg Biosphere Reserve's transitional zone approximately 50km from its origin, traverses the southern section of the Kwalata Nature Reserve (Biosphere Reserve buffer zone) and continues for another 50km before leaving the transitional zone.  16km thereafter it crosses the Waterberg escarpment, drops down to the valley floor and steers east for another 50km before joining the Matimba-Witkop transmission lines.  The total length of Corridor 3 is approximately 165km.

Figure 2.1:	Map showing the alternate transmission line routes identified for consideration in the EIA process

The existing Matimba-Witkop transmission line corridor originates at the Matimba Power Station and travels east for approximately 29 km before reaching the R518.  The lines split at this point and the northern section traverses adjacent to this road for almost 9km while the southern section crosses between two hills.  The two lines meet up shortly thereafter and continue eastward for 30km before entering the transitional, buffer (Touchstone) and core areas (Moepel Farms) of the Waterberg Biosphere Reserve.  After 32 km it crosses the escarpment and continues another 58 km to the proposed Mokopane substation site.  The Matimba-Witkop transmission line covers a distance of over 182 km from Matimba to the proposed substation site.  The section from the proposed substation site to the Witkop substation will be discussed as alternative Corridors 5 and 6 (see below).

Corridor 4, from the proposed Mokopane substation site to the Witkop substation, travels in a south-easterly direction for 11 km before traversing the Percy Fyfe Nature Reserve.  After 6 km it leaves the nature reserve and continues for 16 km across predominantly thicket and bushland before entering the Witkop substation.  The total length of the fourth corridor is approximately 33 km.

Corridors 5 and 6 follow the existing Matimba-Witkop 400kV power lines from the proposed substation site to the Witkop substation.  Corridor 5 (approximately 35 km in length) follows these power lines for the entire length of its alignment, while Corridor 6 veers off after 19 km to follow the Warmbad-Witkop 275 kV line for approximately 17 km.  The total length of Corridor 6 is approximately 37 km.

These alternative transmission line development corridors are evaluated within this Scoping Report (refer to Chapter 5).

### 2.3.1.	Construction Phase

Transmission lines are constructed in the following simplified sequence:

Step 1:	Determination of technically feasible alternatives

Step 2:	EIA input into route selection

Step 3:	Negotiation of final route with affected landowners

Step 4:	Survey of the route (by air)

Step 5:	Determination of the conductor type

Step 6:	Selection of best-suited conductor, towers, insulators, foundations

Step 7:	Final design of line and placement of towers

Step 8:	Issuing of tenders, and award of contract to construction companies

Step 9:	Vegetation clearance and construction of access roads (where required)

Step 10:	Tower pegging

Step 11:	Construction of foundations

Step 12:	Assembly and erection of towers

Step 13:	Stringing of conductors

Step 14:	Rehabilitation of disturbed area and protection of erosion sensitive areas

Step 15:	Testing and commissioning

Construction of the lines proposed as part of the Mokopane Integration Project will take approximately 24 months to complete.  Construction of these lines is anticipated to begin in Confirmed2011.

Construction crews for construction of the transmission power lines will constitute mainly skilled and semi-skilled workers.  No construction workers will reside on site.  It is most likely that construction workers will be accommodated within formal housing within towns surrounding the study area. Construction Camps can be located within the construction area but in consultation and agreement with the landowner. It is mostly preferred that the  construction camps should be in close proximity to the construction site.

### 2.3.2.	Servitude Negotiation and the EIA Process

Transmission power lines are constructed and operated within a servitude (55 m wide for 400kV lines) that is established along the entire length of the power line.  Within this servitude, Eskom Transmission has certain rights and controls that support the safe and effective operation of the power line.  The process of achieving the servitude agreement is referred to as the Servitude Negotiation Process, or simply just the negotiation process.  The following important points relating to the negotiation process should be noted:

- Servitude negotiation is a private matter between Eskom Transmission and the appropriate landowner.

- The negotiation process involves a number of stages (see below), and culminates in the ‘signing’ of a servitude.  Here Eskom Transmission enters into a legal agreement with the landowner.

- The servitude is registered as a ‘right of way’, and Eskom do not purchase the servitude from the landowner.  Compensation measures are agreed in each case.

- The agreements will detail such aspects as the exact location and extent of the servitude, and access arrangements and maintenance responsibilities, as well as any specific landowner requirements.

- The negotiation process may take place at any time in the planning of a new power line.

- This process must be completed (i.e. the agreement must be signed) with the relevant landowner before construction starts on that property.

- The negotiation process is undertaken directly by Eskom Transmission and is independent of the EIA process.  It is important that the aims of the two processes are seen as separate.

The EIA process has become important in the initial planning and route selection of new transmission lines.  For this reason, it is usually preferable that the negotiation process begins after the EIA has been completed.  At this stage there is greater confidence in the route to be adopted, and it would be supported by environmental authorisation.  However, it may be required that the negotiation process begins earlier, and may begin before, or run in parallel with the EIA process.  This may be due to urgent timeframes for the commissioning of the new power line, knowledge of local conditions and constraints, etc.  Eskom Transmission has a right to engage with any landowner at any time, though they do so at risk if environmental authorisation has not been awarded.

### 2.3.3.	The Negotiation Process

Eskom Transmission is responsible for the negotiation process for all new transmission power lines.  It is critical that the process is correctly programmed and incorporated into the planning of a new line.  The negotiation process involves the following steps:

- Initial meeting with the landowner.

- The signing of an ‘option’ to secure a servitude (this indicates that the owner will accept that the power line will traverse his property, subject to conditions to be finalised in the negotiation of the servitude agreement).  An option is valid for one year.

- Once the route is confirmed (i.e. options are signed with the upstream and downstream landowners), the servitude agreement will be finalised with the individual landowners.  This agreement will set out the conditions for the establishment, rehabilitation and maintenance of the servitude, and will be site-specific (as different landowners may have different requirements).  Compensation payments would be made when the servitude is registered at the Deeds Office.

- Once construction is complete and the land rehabilitated to the landowners satisfaction (and as agreed prior to construction), the landowner signs a ‘Final Release’ certificate.  Until the ‘Final Release’ certificate has been signed, Eskom Transmission remains liable for the condition of the land.

- Once the clearance certificate is signed, the responsibility for the power line and servitude is handed over to the regional Eskom Transmission office.

### 2.3.4.	Technical Details of Tower and Transmission Line Designs

All components of a Transmission line are interdependent, but are distinct in the roles which they fulfil.  The primary components include towers, foundations, insulators and hardware, and conductors.

    - Towers

Transmission line conductors are strung on in-line suspension towers and bend (strain) towers.  The structures proposed to be used for the majority of the 765 kV Transmission line are the 765 kV compact cross-rope suspension structures (see Photograph 2.1).  These towers are approximately 50 m in height and a total footprint area of 80 m x 50 m is required for each tower.  The average span between two towers is 400 m.

Photograph 2.1: 	Compact Cross-rope suspension tower typically used along the straight section of a 765 kV Transmission line route

The compact cross-rope suspension tower is typically used along the straight section of the servitude, while the self-supporting angle towers are used where there is a bend in the power line alignment.  Angle towers are cumbersome and more steel-intensive than suspension towers, making them more visually intrusive and expensive to construct.  Therefore, transmission power line routes are planned with as few bends as possible.

    - Servitude Requirements

The servitude width for a 765 kV Transmission line is 80 m.  The servitude is required to ensure the safe construction, maintenance and operation of the line, and thereby entitles Eskom Transmission Division certain rights (e.g. unrestricted access).

Where 765 kV Transmission are constructed in parallel, a minimum separation distance of 60 m is required in order to ensure the reliable operation of both lines.  The minimum vertical clearance to buildings, poles and structures not forming part of the power line must be 10,4 m, while the minimum vertical clearance between the conductors and the ground is 15,0 m.  Any farming activities can be practised under the power line, providing that safe working clearances and building restrictions are adhered to under all circumstances.

The minimum distance of a 765 kV Transmission line structure from a proclaimed public roads is between 60 m and 120 m from the centre line of the road (according to the road type), from the centre of the structure to the centre of the road servitude.  The minimum distance between any part of a tree or shrub and any bare phase conductor of a 765 kV Transmission line must be 10,0 m.

On receipt of an approval of the final corridor by the environmental authorities and after negotiations with landowners, the final definition of the centre line for the Transmission line and co-ordinates of each bend in the line will be determined by the surveyors.  Optimal tower sizes and positions will be identified and verified using a ground survey (in terms of the Environmental Management Plan (EMP) requirements).

A 4-8 m wide strip is generally required to be cleared of all trees and shrubs down the centre of a transmission power line servitude for stringing purposes only.  Any tree or shrub in other areas which will interfere with the operation and/or reliability of the Transmission line must be trimmed or completely cleared.  Vegetation clearance for the proposed Hydra-Gamma 765 kV Transmission line will be minimal due to the characteristic low-growing plant species.  The clearing of vegetation will take place, with the aid of a surveyor, along approved profiles and in accordance with the approved EMP, and in accordance with the minimum standards to be used for vegetation clearing for the construction of the proposed new Transmission line as listed in Table 2.1.

Table 2.1:	Minimum standards to be used for vegetation clearing for the construction of a new transmission power line Confirmed

| Item | Standard | Follow up |
| --- | --- | --- |
| Centre line of the proposed Transmission line | Clear to a maximum (depending on tower type and voltage) of a 4-8m wide strip of all vegetation along the centre line. Vegetation to be cut flush with the ground. Treat stumps with herbicide. | Re-growth shall be cut within 100 mm of the ground and treated with herbicide, as necessary. |
| Inaccessible valleys (trace line) | Clear a 1 m strip for access by foot only, for the pulling of a pilot wire by hand. | Vegetation not to be disturbed after initial clearing – vegetation to be allowed to re-grow. |
| Access/service roads | Clear a maximum (depending on tower type) 6 m wide strip for vehicle access within the maximum 8 m width, including de-stumping/cutting stumps to ground level, treating with a herbicide and re-compaction of soil. | Re-growth to be cut at ground level and treated with herbicide as necessary. |
| Proposed tower position and proposed support/stay wire position | Clear all vegetation within proposed tower position in an area of 20 x 20 m (self-supporting towers) and 40 x 40 m (compact cross-rope suspension towers) around the position, including de-stumping/cutting stumps to ground level, treating with a herbicide and re-compaction of soil. Allow controlled agricultural practices, where feasible. | Re-growth to be cut at ground level and treated with herbicide as necessary. |
| Indigenous vegetation within servitude area (outside of maximum 8 m strip) | Area outside of the maximum 8 m strip and within the servitude area, selective trimming or cutting down of those identified plants posing a threat to the integrity of the proposed sub-transmission line. | Selective trimming |
| Alien species within servitude area (outside of maximum 8 m strip) | Area outside of the maximum 8 m strip and within the servitude area, remove all vegetation within servitude area and treat with appropriate herbicide. | Cut and treat with appropriate herbicide. |

Once the centre line has been cleared, the contractor’s surveyor will peg every tower position and marks the crossing point with existing fences for new gate installation.  Where required, once the tower positions have been marked, the vegetation clearing team will return to every tower position and clear vegetation (in accordance with the specification outlined in the Environmental Management Plan (EMP)) for assembling and erection purposes.

    - Foundations

The choice of foundation is influenced by the type of terrain encountered, as well as the underlying geotechnical conditions.  Geotechnical requirements for all tower types are catered for by using various foundation types, which are designed to withstand conditions varying from hard rock to waterlogged marshes.  The main types of foundations include piles, pad-and-chimney, and rock anchors.  The actual size and type of foundation to be installed will depend on the type of tower to be erected, and the actual sub-soil conditions.  Strain towers require more extensive foundations for support than in-line suspension towers, which contribute to the construction expenses.

The construction of foundations is the slowest part of the line construction, and is typically started some time ahead of tower erection.  Prior to filling of the foundations and tower erection, excavated foundations are covered or fenced in, in order to safe-guard unsuspecting animals and people from injury.  The foundations also represent the biggest unknown in the cost and construction time, since access to the tower sites is required for earth-moving machinery and concrete.

All foundation excavations are back-filled, stabilised through compaction, and rehabilitated at ground level.

    - Insulators and Hardware

The insulators and hardware are used to connect the conductors to the towers.  The main types are glass, porcelain, and composite insulators.

Glass and porcelain have been used for many years, and are the most common.  They are, however, heavy and susceptible to breakage by vandals, as well as contamination by pollution.  Composite insulators have a glass-fibre core with silicon sheds for insulation.  The composite insulators are light-weight and resistant to both vandalism and pollution.  They are, however, more expensive than the more common glass insulators.

    - Conductors

The conductors are made of aluminium with a steel core for strength.  Power transfer is determined by the area of aluminium in the conductors.  Conductors are used singularly, in pairs, or in bundles of three, four or six.  The choice is determined by factors such as audible noise, corona, and electro-magnetic field mitigation.

Many sizes of conductor are available, the choice being based on the initial and life-cycle costs of different combinations of size and bundles, as well as the required load to be transmitted.

2.4.	Project Operation Phase

The expected lifespan of the proposed transmission power line is between 35 and 40 years, depending on the maintenance undertaken on the power line structures.

During the life-span of the transmission power line, on-going maintenance is performed.  Power line inspections are undertaken on an average of 1 – 2 times per year, depending on the area.  During this maintenance period, the power line is accessed via the access routes, as agreed with affected landowners during the negotiation phase.  Maintenance of the power line is required to be undertaken in accordance with the specifications of the Environmental Management Plan (EMP) which is to form part of the EIA Report.

The creation of additional employment opportunities during the operational phase of the power line will be limited, and will be restricted to skilled maintenance personnel employed by Eskom.

### 2.3.1.	Servitude Maintenance Responsibilities

The management of a transmission power line servitude is dependent on the details and conditions of the agreement between the landowner and Eskom Transmission, and are therefore site-specific.  These may, therefore, vary from one location to another.  However, it is a common occurrence that there is a dual responsibility for the maintenance of the servitude:

- Eskom Transmission will be responsible for the tower structures, maintenance of access roads, watercourse crossings, and gates and fences relating to servitude access.

- The landowner will retain responsibility for the maintenance of the land and land use within the servitude (e.g. cropping activities, veld management, etc.).

Exceptions to the above may arise where, for example dual use is made of the access roads and gates or specific land use limitations are set by Eskom Transmission within the servitude which directly affects the landowner (e.g. forestry).  Maintenance responsibilities are, ultimately, clearly set out in the servitude agreement.

Compensation will be based on present day property valuations for all properties obtained from registered evaluators.  Eskom only pays compensation for the strip of land that is affected at 100% of present day property value.  In cases where properties are significantly affected, Eskom may consider purchasing the whole property at present day market value.  All improvements will be valued.  Sentimental value is not considered in any valuations as it is not measurable.  Valuations are done according to the Expropriation Act.